## ProductBackLog
Project Name: Happy Tails Group Members: Semih Öztürk, Mirza Kerem Kılıç, Melike Gülmine Kırpat, Özge Öztürk, Hüseyin Günçiçek, Arda Özkaranfil, İdil Buse Zengin
# | Product BackLog
1 | Initialize the database to store the users, shelters and registered animals
2 | Offer detailed information pages for each animal including characteristics, health status, and background information
3 | Enable users to contribute specific items such as food, medicine, or supplies to selected animals
4 | Create a section where users can explore shared adoption experiences and success stories
5 | Allow users to schedule visits for adoption based on available time slots and shelter availability
6 | Allow users to notify shelter staff about urgent situations observed during live monitoring
7 | Develop an OpenAI based recommendation feature that suggests suitable animals based on user-provided information
8 | Provide real-time video access from animals and shelter environments remotely with Agora
9 | Implement an interface for users to access the video streaming
10 | Enable shelters to maintain and update medical and vaccination information for animals
11 | Provide a system for shelters to monitor incoming donations and assign them to specific animals
12 | Support user registration and login to access system features/Create a registration flow for users to provide personal detail and agree to PDPL (KCKK) terms.
13 | Ensure the live streaming feature operates consistently with minimal interruptions to provide continuous monitoring access
14 | Protect user data through secure storage and encryption with SHA-256
15 | Implement an OpenAI API based mechanism to review and control user-generated content to prevent inappropriate or irrelevant submissions
16 | Implement regular data backup procedures and enable quick recovery of system data in case of failures
17 | Automatically inform the user with a notification when there is a planned maintanance
18 | Ensure the application operates smoothly across modern web browsers (Chrome v110+, Safari v15+, Firefox v105+), iOS (v15 and above) and Android (v10 and above).
19 | Optimize the system architecture to support 5,000 concurrent users and 100 shelters while maintaining a maximum response time of 2 seconds
20 | Ensure all financial transactions are handled through Stripe

## Sprint-1
SPRINT-1
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer | UI Design | Ready to Start | Medium | 2026-04-01 | 2026-04-07 | 5 | Create simple and user-friendly interface structure
Developer, Product Owner | Database Structure Design | Ready to Start | High | 2026-04-06 | 2026-04-08 | 3 | Designing database schema for animals, users, shelters, donations, and appointments
Developer | User Registration and Authentication System | Ready to Start | Medium | 2026-04-09 | 2026-04-10 | 2 | Implement user sign-up, login, and secure authentication
Developer | Animal Listing Page | Ready to Start | Medium | 2026-04-09 | 2026-04-14 | 4 | Display available animals with basic information
Developer | Animal Detail Page | Ready to Start | Medium | 2026-04-15 | 2026-04-20 | 4 | Show detailed animal profiles including health and background
Developer | Adoption Appointment Scheduling | Ready to Start | Low | 2026-04-15 | 2026-04-20 | 4 | Allow users to book adoption appointments based on available time slots
14
BACKLOG
As a Visitor, I want to sign up and log in securely, so that I can access personalized features like tracking my donations and appointments.
STATUS: Ready to Start
As a User, I want to view a list of all available animals, so that I can quickly browse through the pets looking for a home.
STATUS: Ready to Start
Visitor
User

## Sprint-2
SPRINT-2
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer | Animal Search, Filtering & AI Recommendation | Not Started | Medium | 2026-04-21 | 2026-04-23 | 3 | Implement filtering options based on animal type/age, and develop an OpenAI based recommendation feature that suggests suitable animals based on user data.
Developer | Medical Management | Not Started | Medium | 2026-04-24 | 2026-04-29 | 4 | Develop a module for shelters to update and track medical records and vaccination schedules for animals.
Developer | Item Donation | Not Started | Medium | 2026-04-30 | 2026-05-01 | 2 | Enable quick selection and contribution of money, food, medicine or supplies to specific animals.
9
BACKLOG
User
Dev
Potential Adopter
As a User, I want to filter animals by type, age, and health status, so that I can easily find a pet that matches my lifestyle and preferences.
STATUS : Not Started
As a Potential Adopter, I want to view high-quality images and detailed profile stories, so that I can build an emotional connection with the animal before visiting.
STATUS : Not Started

## Sprint-3
SPRINT-3
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer | User stories sharing platform | Not Started | Low | 2026-05-04 | 2026-05-06 | 3 | A basic forum allowing users to share their experiences.
Developer | OpenAI based user stories content control | Not Started | Medium | 2026-05-07 | 2026-05-07 | 1 | Apply an AI-based tool for controlling the content submissions.
Developer | Urgent Notifications | Not Started | Medium | 2026-05-08 | 2026-05-08 | 1 | Implement a real-time alert system for users to report emergencies to shelter staff during live streams.
Developer | Live Monitoring | Not Started | Medium | 2026-05-11 | 2026-05-18 | 6 | Integrate Agora SDK to provide real-time video streaming of animals and shelter environments.
11
BACKLOG
User
Donor
As a Donor, I want to make secure online payments via Stripe, so that I can easily transfer funds to support the shelter's needs.
STATUS: Not Started
As a user, I want to access a real-time alert system so that I can immediately report emergencies to shelter staff during live streams.
STATUS: Not Started

## Sprint-4
SPRINT-4
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer | System Availability & Architecture Optimization | Not Started | High | 2026-05-19 | 2026-05-25 | 5 | Maintain high uptime, implement automated maintenance notifications and optimize architecture to support 5000 concurrent users with max 2s response time.
Developer | Encode User Data with SHA-256 | Not Started | Medium | 2026-05-19 | 2026-05-19 | 1 | Protect sensitive information by hashing.
Developer | Data backup | Not Started | High | 2026-05-19 | 2026-05-19 | 1 | Stored data will be backed up.
Developer | Test before deployment | Not Started | High | 2026-05-22 | 2026-06-01 | 7 | Final test of the software before deployment.
10
BACKLOG
As a customer, I want to recommend this app in my local animal lover community.
STATUS: Not Started
As a User, I want the software to operate smoothly across different devices and browsers, so that I can access the system regardless of the platform I am using.
STATUS: Not Started
User
Customer
As a Developer, I want the system to have high uptime and automated maintenance alerts, so that I can rely on the service being available whenever I need to use it.
STATUS: Not Started
Dev

## KeyDropdowns
KEY DROPDOWNS - DO NOT DELETE
PRIORITY KEY | STATUS KEY
High | In Progress
Medium | Ready to Start
Low | Complete
On Hold
Testing
Not Started

## Templates
TEMPLATES
ASSIGNED TO | KANBAN CARDS
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here